## Sheet1
Test Executed By | Execution Date | Test Title | Test Steps | Expected Result | Actual Result | Status | Comments
Neha Natesh | 2022-03-18 | Input Validity | Check each input with errors to see if error flag is working. | Mail is not sent to employees with corrupt/wrong data | Mail was not sent to employees with wrong data | Pass | All error handling worked as expected.
Neha Natesh | 2022-03-20 | Input Validity | Check with atleast one wrong input for every employee | Process is terminated since no employee with correct input data exists | Process terminated | Pass | Filtering data table to terminate process worked as expected
Neha Natesh | 2022-03-20 | Input Validity | Check with all inputs being correct | Mails sent to all the employees | All mails sent | Pass | Mails were sent to all the employees
Neha Natesh | 2022-03-20 | File not found | Check for file not found in all the workflows | Process is terminated | Process was terminated | Pass | Process was terminated when file was not found in activities.
Neha Natesh | 2022-03-20 | Input Validity | Skip sending mails to employees with error data but send mails to employees with correct data without terminating the process. | Mails sent to only employees with all data being correct | Mails sent to employees with correct data | Pass | Process completed without terminating when error found in input file for few employees.
Najma Fathima | 2022-03-20 | Input Validity | Checking the operation with Two wrong inputs | payslips not created to the employees with wrong input | Pay slips not created and the error was recorded | Pass | Completed the execution by sending emails only to the employees whose payslips were created.
Najma Fathima | 2022-03-20 | Output | Once the emails are sent to the employees whose payslips were created. | Email to be sent to the HR with the status file of the emails successfully sent and status of the emails not sent. | Email to the HR sent successfully. | Pass | Execution complete and successful.
Shradha Sarap | 2022-03-19 | Input Validity | Check with all wrong input for every employee | Process is terminated since no employee with correct input data exists | Process terminated | Pass | Process terminated and proper logs generated
Shradha Sarap | 2022-03-20 | Input validity | Input data file removed | Terminate the flow as no input file available and log the error | Process terminated | Pass | Process terminated and proper logs generated